## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sidram Patil | 2026-02-20 | LangChain environment setup failed due to dependency conflicts | Sprint 1 | Devender Pratap | Configuration | Resolved dependency issues and installed compatible versions | 2026-02-21 | Closed | Tested successfully
2 | Sidram Patil | 2026-02-21 | LLM connection failed while integrating Groq API | Sprint 1 | Devender Pratap | API | Configured API key and environment variables correctly | 2026-02-21 | Closed | Connection verified
3 | Sidram Patil | 2026-02-23 | Agent not generating correct responses for simple queries | Sprint 1 | Devender Pratap | Functional | Improved prompt structure and agent configuration | 2026-02-24 | Closed | Output validated
4 | Sidram Patil | 2026-03-01 | Weather tool not returning correct city data | Sprint 2 | Devender Pratap | Functional | Fixed API request and response parsing logic | 2026-03-02 | Closed | Tested successfully
5 | Sidram Patil | 2026-03-03 | Agent fails when chaining multiple tools, incorrect execution flow | Sprint 2 | Devender Pratap | Functional | Fixed tool chaining logic in LangChain orchestration | 2026-03-04 | Closed | Workflow validated
6 | Sidram Patil | 2026-03-06 | Agent asking user which tool to use instead of auto selection | Sprint 2 | Devender Pratap | Logic | Improved system prompt to enforce tool usage | 2026-03-07 | Closed | Working correctly
7 | Sidram Patil | 2026-03-09 | Response time too high for multi-agent tasks | Sprint 2 | Devender Pratap | Performance | Optimized prompt handling and reduced token usage | - | Open | Needs further tuning
8 | Sidram Patil | 2026-03-14 | Memory not storing previous conversation context | Sprint 3 | Devender Pratap | Functional | Fixed shared memory configuration and update logic | 2026-03-15 | Closed | Context working
9 | Sidram Patil | 2026-03-16 | Router incorrectly classifying simple and complex queries | Sprint 3 | Devender Pratap | Logic | Refined routing prompt and decision rules | 2026-03-17 | Closed | Accuracy improved
10 | Sidram Patil | 2026-03-18 | Agent stops at Thought or Action without final answer | Sprint 3 | Devender Pratap | Functional | Added final answer enforcement and output handling | 2026-03-19 | Closed | Issue resolved
11 | Sidram Patil | 2026-03-25 | Flask API not returning proper JSON response | Sprint 4 | Devender Pratap | Backend | Fixed API route and response formatting | 2026-03-26 | Closed | API verified
12 | Sidram Patil | 2026-03-28 | UI not showing agent output correctly | Sprint 4 | Devender Pratap | UI | Fixed frontend rendering and JavaScript fetch logic | 2026-03-29 | Closed | Verified by testing
13 | Sidram Patil | 2026-04-01 | Database not saving chat history consistently | Sprint 4 | Devender Pratap | Database | Corrected SQLite queries and commit handling | 2026-04-02 | Closed | Data stored successfully
14 | Sidram Patil | 2026-04-03 | PDF upload not extracting text properly | Sprint 4 | Devender Pratap | Feature | Handled null pages and limited extraction size | 2026-04-04 | Closed | Feature working
15 | Sidram Patil | 2026-04-04 | Final output missing in some agent responses | Sprint 4 | Devender Pratap | Functional | Used safe output extraction method (.get) | 2026-04-05 | Closed | Output fixed
16 | Sidram Patil | 2026-04-05 | UI response delay during multiple requests | Sprint 4 | Devender Pratap | Performance | Optimized frontend rendering and API calls | 2026-04-05 | Open | Needs optimization

## Sheet2
Logical
User Interface
Maintainability
Standards
Others